# ImpactMap AI: Team Work Division, Anon

Version 1.0 · Built on Functional Documentation v0.2 · Dagim (tech lead and backend lead), Anon (frontend lead), Yagi (support developer) · Written Friday October 23, 2026 · Submission deadline Wednesday October 28, 2026 · This copy for Anon: Part C (common), Part A (Anon) and Part S (schedule)

## How to use this document

This is your personal copy of the team work division. It contains Part C (common), Part A (Anon) and Part S (schedule). The other two team members have their own copies with the same Part C and Part S, so the common rules, contracts and schedule are identical for all three of you. Read Part C completely today, then your own part, then Part S. Where the text mentions another person's part, that part is in their copy; ask them for it if you need to see it, and skim it once so you know what they are waiting for from you.

- Part C: common rules, repository structure, shared naming contracts, API contract, Git rules, configuration, progress files.

- Part A: Anon (frontend lead, map application, mock server, tests, demo).

- Part S: day-by-day schedule, the cut-line, final checklists.

How tasks are written, and why

- MANUAL blocks are things a person must do by hand: accounts, tokens, console clicks, installs, downloads. They are written step by step with current information. Do these yourself and follow the steps in order. Do not ask a different AI for these steps, because it will not know our setup.

- BUILD SPEC blocks describe what a code file or screen must do, with exact names and contracts. These are meant to be given to an AI coding assistant together with the context packet in section C8, in small pieces, one file at a time. The spec and contracts are the protection against two people's code not fitting together.

- CODE blocks are exact code or commands, used where a mistake would break another person's work or where precision matters (hashing, contracts, infrastructure roles).

- [checked] means the fact was confirmed on October 23 against current documentation. [verify] means confirm it at that step and write down what you saw.

- Never paste a secret (AWS keys, bot tokens, passwords) into an AI chat, a chat group, an issue, or the repository.

Where this document refines v0.2 (on purpose, so nobody is surprised)

| # | v0.2 said | This document does | Reason |
| --- | --- | --- | --- |
| 1 | Lambda arm64 | Lambda x86_64 | Building arm64 container images on common laptops and the default CI runner needs emulation; x86_64 is free of that risk and costs nothing extra inside the free allowance. |
| 2 | Web build knows the API URL | The web app reads a runtime file /config.json | The API and CDN addresses only exist after deployment; a runtime file avoids a build-order problem. |
| 3 | One SegmentRisk list | A compact columnar segments file plus a separate segment explain endpoint | 30,000 segments with reasons would be a very large response. |
| 4 | ECR repository in the Data stack | CDK's own asset repository | Less to build; same result. Cleanup is documented. |
| 5 | Reserved concurrency on every function | Reserved concurrency only if the account quota allows it; API throttling always | New accounts can have a low concurrency quota that blocks reserved concurrency [verify in section D2]. |
| 6 | Team gets IAM access | Only Dagim has AWS access; Anon and Yagi deploy through CI | Least privilege, and fewer accounts to protect. |
| 7 | Region not chosen | eu-central-1 (Frankfurt) | Close to Ethiopia among regions that work without opt-in. Fallback eu-west-1. |

Timeline reality. Today is October 23. The hard deadline is October 28, so there are five working days including today (23, 24, 25, 26, 27) and the 28th is buffer. Part S converts that into hours. The Day-1 work of the 22nd is finished first thing this morning.

# PART C. COMMON SECTION (everyone)

## C1. Team work division overview

| Member | Role | Owns | Depends on | Share of work |
| --- | --- | --- | --- | --- |
| Dagim | Tech lead and backend lead | Repo and contracts, AWS account, infrastructure code, CI/CD, data pipeline, labels, ML model and evaluation, graph engine, API, worker, observability, load test, teardown, README technical sections, architecture diagram | Nobody for the first deliverable; the labels depend on the data gate | About 55 percent |
| Anon | Frontend lead | Web application (map, scenario panel, results, compare, drawers, cascade, evidence panel), typed API client, mock server, basemap extract, translation-ready UI, web tests, phone performance, demo flow and video | Dagim's contracts and fake API (today), real API (Oct 25), evidence JSON (Oct 26) | About 35 percent |
| Yagi | Support developer | Four small tasks (Part Y): data catalog, glossary and About text, facility classification sheet, tester operations | Dagim's source list (today), facility export (Oct 24), Anon's component for static pages (Oct 26) | About 10 percent |
| Testers | Product testers | Scripted rounds, data spot checks, demo audience | A live URL | n/a |

FIRST ACTION TODAY: one 60-minute screen-share session with all three. Dagim shares the screen. Together: create the GitHub repository, add the skeleton folders from C2, add CONTRACTS.md, set the Git rules from C5, and push to main. Then everyone branches off. This protects the foundation.

### C1.1 What unblocks what (critical path)

- Today by 12:00: Dagim pushes CONTRACTS.md, contracts/openapi.yaml and contracts/examples/. Anon starts from these with a mock server.

- Today by end of day: Dagim deploys the walking skeleton: a fake API behind API Gateway returning the example JSON. Anon points the app at it.

- Tomorrow, October 24: Dagim exports facilities.csv for Yagi's classification sheet.

- October 25: real model and engine are wired in. Anon switches from fake to real results without changing code, because the contract does not change.

- October 26: evidence JSON available for the evidence panel; demo scenarios precomputed.

### C1.2 Rules of engagement

- Two status lines a day in the team chat: morning (what I do today, what blocks me) and evening (what is done, what is not). One 15-minute call at a fixed time.

- A blocker is reported within one hour. Nobody waits more than two hours on another person without saying so.

- Contract changes (names, shapes, endpoints) go through Dagim only, are announced in the chat, and are added to CONTRACTS.md the same hour. Screen and component decisions belong to Anon. If you disagree, Dagim decides within ten minutes.

- Nobody edits a file owned by another person without telling them. Ownership is in C2 and in the CODEOWNERS file.

- Commit small and often, from everyone, from today. Commit history is part of the judged documentation score.

### C1.3 Definition of done (for every task)

- It works on the live URL or in the local run described in the task.

- It has at least one test or a written manual check in its MODULE file.

- CI is green on the pull request.

- The contract still matches (no renamed field).

- The MODULE file is updated and a teammate knows it is done.

## C2. Repository structure

The repository must follow this structure exactly. Names matter, because the infrastructure code, the API and the web app import by these paths. The repository is public from the first commit (the handbook requires it, and public repositories get free CI minutes) [verify the free CI minutes on our GitHub account]. That is why nothing secret may ever be committed.

impactmap/                           root of the GitHub repo
  README.md                          judges read this first (Dagim, Yagi skeleton)
  LICENSE                            MIT
  CONTRACTS.md                       copy of section C3 (single source of truth)
  Makefile                           one-word commands: make test, make lint, make deploy
  pyproject.toml                     ruff and pytest settings
  requirements-dev.txt               tools for local work
  .python-version                    3.12
  .nvmrc                             22
  .editorconfig  .gitignore  .env.example  .gitleaks.toml
  .github/
    CODEOWNERS                       who owns which folder
    pull_request_template.md
    ISSUE_TEMPLATE/                  bug.yml, confusing.yml, data-error.yml   (Yagi)
    workflows/                       ci.yml, deploy.yml, teardown.yml (manual only)
  contracts/
    openapi.yaml                     API contract (Dagim)
    examples/                        one sample JSON per shape (Dagim)
  docs/
    definitions.md                   D1 to D12 from the functional doc, frozen (Dagim)
    aws-account.md  cost.md  model-card.md  architecture.png
    data-catalog.csv                 (Yagi)      glossary.md  (Yagi)
    testing/tester-script.md         (Yagi)
    adr/                             short decision records, 0001-region.md ...
    MODULE_SETUP.md  MODULE_DATA.md  MODULE_ML.md  MODULE_ENGINE.md
    MODULE_API.md    MODULE_INFRA.md  MODULE_WEB.md  MODULE_SUPPORT.md
  data/
    README.md                        how data is built (Dagim)
    raw/  processed/                 gitignored, never committed
  pipeline/                          offline data build (Dagim)
    impactmap_pipeline/              download.py osm_graph.py facilities.py communities.py
                                     terrain.py rainfall.py labels.py tiles.py publish.py
    tests/
  ml/                                training and evaluation (Dagim)
    prepare_labels.py  train.py  evaluate.py  baselines.py  calibrate.py  export_model.py
    reports/                         evaluation outputs (small files only)
  packages/
    impactmap_core/                  shared Python package, no cloud imports (Dagim)
      pyproject.toml
      src/impactmap_core/            __init__.py (version) schemas.py scenario.py hashing.py
                                     features.py graph_io.py closure.py montecarlo.py metrics.py
                                     ranking.py explain.py whatif.py
      tests/
  services/
    api/                             FastAPI app for API Gateway (Dagim)
      app/main.py  app/routers/  app/deps.py  requirements.txt  tests/
    worker/                          container image for the heavy job (Dagim)
      Dockerfile  handler.py  requirements.txt
  infra/                             AWS CDK in Python (Dagim)
    app.py  cdk.json  requirements.txt
    stacks/                          data_stack.py web_stack.py api_stack.py config_stack.py
                                     observability_stack.py  (P1: scheduler_stack.py auth_stack.py)
  web/                               React application (Anon)
    package.json  vite.config.ts  index.html  public/config.json
    src/                             see section A1
  tests/
    integration/                     API tests against the live stack (Dagim)
    load/                            k6 scripts (Dagim)
    e2e/                             Playwright tests (Anon)
  scripts/                           smoke.sh  make_demo.py  build_all.sh (Dagim)

Who owns what (also written into .github/CODEOWNERS): Dagim owns /infra, /services, /packages, /pipeline, /ml, /contracts, /scripts, /tests/integration, /tests/load, /.github/workflows. Anon owns /web, /tests/e2e. Yagi owns /docs/data-catalog.csv, /docs/glossary.md, /docs/testing, /.github/ISSUE_TEMPLATE. Everything else is Dagim's unless stated.

## C3. Shared naming contracts

These are exact. A renamed field breaks the other person's code. They are copied into CONTRACTS.md and are the first thing to read when something does not fit.

### C3.1 Identifiers, units and formats

| Item | Format | Example and rule |
| --- | --- | --- |
| region_id | lowercase snake case | pilot_01 until the data gate tonight; then renamed once to the real area (for example awash_01); never changes after that |
| segment_id | integer, 0 or more | 18452. Assigned once by the pipeline, stable inside one data_version. In map tiles it is the numeric property segment_id. |
| facility_id | fac_ plus 5 digits | fac_00017 |
| community_id | com_ plus 5 digits | com_00231 |
| catchment_id | integer | 7 |
| job_id | UUID v4 string | 3f2a9c1e-5b7d-4e8a-9c21-7d4e5f6a8b90 |
| cache_key | 32 lowercase hex characters | built by the function in section D8, nobody else computes it |
| scenario slug | lowercase kebab case | awash-2020-replay, wet-week-heavy-storm |
| Coordinates | [longitude, latitude], WGS84 (EPSG:4326), 5 decimals | GeoJSON order. Never latitude first. |
| Time | ISO 8601 UTC string | 2026-10-25T08:30:00Z ; dates as 2026-10-25 |
| Probability | float from 0 to 1, rounded to 4 decimals | 0.2371 |
| People | integer, always an estimate | people_affected_est |
| Travel time | minutes as float, 1 decimal | 47.5 |
| Length and distance | metres as integer | length_m, snap_distance_m |
| Rainfall | millimetres as float | daily_rain_mm |
| JSON field names | snake_case everywhere | The web app uses the same names. No camelCase conversion layer. |
| Python | snake_case modules and functions, PascalCase classes |  |
| TypeScript | PascalCase component files (FacilityDrawer.tsx), camelCase variables, hooks named useXxx | field names from the API stay snake_case |

### C3.2 Enum values (exact strings)

| Name | Allowed values |
| --- | --- |
| hazard | flood, landslide |
| evidence_level | validated, limited, heuristic |
| failure_mode | independent, correlated |
| spatial.type | uniform, gradient, cell |
| storm_shape | even, front_loaded, mid_peak, back_loaded |
| wetness (antecedent class) | dry, normal, wet |
| job status | queued, running, done, failed |
| facility level | hospital, health_center, clinic |
| road_class | motorway, trunk, primary, secondary, tertiary, unclassified, residential, track, other |
| quality_flag | ok, low_road_density, long_snap, weak_source |
| layer mode (web only) | exposure, closure |
| error code | VALIDATION_ERROR, NOT_FOUND, JOB_FAILED, JOB_TIMEOUT, RATE_LIMITED, VERSION_MISMATCH, INTERNAL_ERROR |

### C3.3 Version strings

| Name | Format | Example | Set by |
| --- | --- | --- | --- |
| data_version | d + yyyymmdd + one letter | d20261025a | pipeline publish step |
| model_version | m + yyyymmdd + one letter | m20261026a | export_model.py |
| engine_version | semantic version from impactmap_core.version | 0.1.0 | package |
| app_version | short git commit | 9fa31c2 | CI |

Every API result carries the first three. A cache hit requires all three to match (section D8).

### C3.4 Storage, tables and resource names

| Resource | Exact name or key |
| --- | --- |
| Region | eu-central-1 |
| Data bucket | impactmap-data-ACCOUNTID (ACCOUNTID is the 12-digit AWS account number) |
| Web bucket | impactmap-web-ACCOUNTID |
| Public prefix in data bucket (served by CloudFront under /data/*) | data/ ; inside: data/DATA_VERSION/ for map data and evidence, data/results/CACHE_KEY/ for results, data/demo/SLUG/ for precomputed cascades, data/basemap/ for the basemap |
| Private prefix (worker and API only, never public) | private/DATA_VERSION/ for graph and feature arrays, private/models/MODEL_VERSION/ for the model |
| Jobs table | impactmap-jobs ; partition key job_id (string) ; time-to-live attribute expires_at |
| Cache table | impactmap-cache ; partition key cache_key (string) ; attributes result_prefix, versions, created_at |
| API function | impactmap-api |
| Worker function | impactmap-worker |
| API | one API Gateway HTTP API named impactmap-http, default stage, no stage prefix in URLs |
| CloudFormation stacks | ImpactMapDataStack, ImpactMapWebStack, ImpactMapApiStack, ImpactMapConfigStack, ImpactMapObsStack, plus ImpactMapCiStack (deployed by hand once, never by CI) (P1: ImpactMapSchedulerStack, ImpactMapAuthStack) |
| Tags on every resource | Project=ImpactMap, Owner=dagim |
| CloudWatch log retention | 14 days |
| GitHub OIDC deploy role | impactmap-gha-deploy |

### C3.5 API endpoints (exact paths, no trailing slash)

The API is one API Gateway HTTP API in front of the impactmap-api function. All bodies and responses are JSON. All responses carry the header x-request-id. Dagim writes contracts/openapi.yaml from this section today; Anon generates the typed client from that file.

| Method | Path | Purpose | Success | Errors |
| --- | --- | --- | --- | --- |
| GET | /health | Liveness check | 200 with status ok | none |
| GET | /meta | Versions, region, data catalog summary, limits (max days, samples) | 200 | 500 |
| GET | /regions | List of regions with bounding box | 200 | 500 |
| GET | /hazards | Hazards with evidence level and label type | 200 | 500 |
| GET | /scenarios/library | Named scenarios (manual and replay) | 200 | 500 |
| POST | /scenarios | Create and run a scenario. Cached: result is returned at once. Not cached: a job is created. | 200 (cached, Job with status done) or 202 (Job queued) | 400 VALIDATION_ERROR, 429 RATE_LIMITED |
| GET | /jobs/{job_id} | Poll a job | 200 | 404 NOT_FOUND |
| GET | /results/{cache_key} | Result summary with ranking | 200 | 404 NOT_FOUND |
| GET | /results/{cache_key}/segments | Columnar segment probabilities for painting the map | 200 | 404 NOT_FOUND |
| GET | /segments/{segment_id}/explain?cache_key=... | Reasons one segment is risky | 200 | 404 NOT_FOUND |
| GET | /facilities/{facility_id}/explain?cache_key=... | Why a facility ranks where it does, alternative route | 200 | 404 NOT_FOUND |
| POST | /whatif | Force segments open or closed on top of a finished result | 200 or 202 as POST /scenarios | 400, 404 |
| GET | /compare?a=...&b=... | Compare two finished results | 200 | 404 NOT_FOUND |
| GET | /backtests | Past events with predicted versus observed summaries | 200 | 500 |
| GET | /model-card | Model card text and key numbers | 200 | 500 |

Static files (served by CloudFront, not by the API): /config.json, /data/DATA_VERSION/meta.json, /data/DATA_VERSION/facilities.geojson, /data/DATA_VERSION/communities.geojson, /data/DATA_VERSION/tiles/roads.pmtiles, /data/DATA_VERSION/evidence/evaluation.json, /data/basemap/ethiopia.pmtiles, /data/demo/index.json and /data/demo/SLUG/step_N.json, /data/results/CACHE_KEY/summary.json and segments.json.

### C3.6 JSON shapes (field by field)

Types: str, int, float, bool, list[x], obj. A question mark means the field can be null.

Scenario (body of POST /scenarios)

| Field | Type | Rule |
| --- | --- | --- |
| hazard | str | flood (landslide only when the feature flag is on) |
| region_id | str | must exist in /regions |
| start_date | str | YYYY-MM-DD |
| daily_rain_mm | list[float] | length 1 to 10, each 0 to 400 |
| antecedent_30d_mm | float | 0 to 600 |
| spatial | obj | type plus params. uniform: no params. gradient: direction_deg 0 to 359, ratio 0.2 to 1.0. cell: center [lon, lat], radius_km 5 to 200. |
| closure_factor | float | 0.0 to 1.0, default 1.0 (assumed closure, section 1.2 of the functional doc) |
| failure_mode | str | independent (default); correlated only when the flag is on |
| n_samples | int | 50 to 500, default 200 |
| seed | int | default 42 |
| forced_closed | list[int] | segment_ids, default empty |
| forced_open | list[int] | segment_ids, default empty; must not overlap forced_closed |

Job (response of POST /scenarios, POST /whatif, GET /jobs/{job_id})

| Field | Type | Meaning |
| --- | --- | --- |
| job_id | str |  |
| status | str | queued, running, done, failed |
| cache_key | str | result identity |
| submitted_at, started_at?, finished_at? | str | ISO UTC |
| result_url? | str | set when done: path under /data/results/CACHE_KEY/ |
| error? | obj | code, message, field?, request_id |

ResultSummary (GET /results/{cache_key} and data/results/CACHE_KEY/summary.json)

| Field | Type | Meaning |
| --- | --- | --- |
| cache_key | str |  |
| versions | obj | model, data, engine strings |
| hazard, evidence_level | str | enums |
| scenario | obj | echo of the canonical Scenario |
| base_cache_key? | str | set when produced by a what-if |
| computed_at | str | ISO UTC |
| region_totals | obj | people_cut_off, people_degraded (each obj with mean, p10, p90, floats), facilities_isolated_expected (float) |
| ranking | list[FacilityImpact] | sorted by rank ascending |
| top_communities | list[CommunityImpact] | at most 50, by people affected |
| assumptions | obj | speeds_kmh by road_class, closure_factor, degraded_ratio (2.0), poor_baseline_minutes (120), failure_mode |

FacilityImpact: facility_id, name, level, p_isolation, p10, p90, people_affected_est (int), baseline_minutes?, poor_baseline_access (bool), alt_route? (obj: minutes, segment_ids), rank (int), rank_delta? (int, versus baseline ordering), snap_distance_m (int), source (str), quality_flag.

CommunityImpact: community_id, name?, people_est (int), p_cut_off, p_degraded, expected_minutes?, baseline_minutes?, poor_baseline_access (bool), snap_distance_m (int), quality_flag.

Segments (columnar) (GET /results/{cache_key}/segments): cache_key, n_total (int), sparse_threshold (float, 0.005), segment_ids (list[int]), exposure_prob (list[float]), closure_prob (list[float]). The three lists have the same length and the same order. A segment that is not listed has probability 0. This keeps the payload small and lets the map paint only what matters.

SegmentExplain: segment_id, name?, road_class, length_m, exposure_prob, closure_prob, quality_flag, top_reasons (list of obj: feature, label, contribution), where label is plain English such as Low ground next to a river.

FacilityExplain: facility_id, rank, rank_delta?, p_isolation, why (list of at most 3 obj: segment_id, lift, closure_prob, text), alt_route? (obj: minutes, segment_ids, geometry as a GeoJSON LineString with [lon, lat] coordinates), sentences (list[str], template text for the UI to show as is).

WhatIf (request): base_cache_key, forced_closed (list[int]), forced_open (list[int]). Response: Job.

Compare (response): a, b (the two cache_keys), region_totals_a, region_totals_b, people_cut_off_delta (float), rank_changes (list of obj: facility_id, rank_a, rank_b).

Error (every non-2xx response): an object with one field error, itself an object with code, message, field?, request_id.

Runtime config (/config.json): api_base_url, data_base_url, region_id, data_version, model_version, app_version, features (obj of bool: correlated_mode, landslide, forecast, accounts). The UI hides anything whose feature flag is false.

Evidence file (data/DATA_VERSION/evidence/evaluation.json), produced by ml/evaluate.py: evidence_level, label_rung (L0 to L3), n_events (int), events (list of obj: event_id, name, dates, country, source, split), metrics (obj: model, b0, b1, b2; each with pr_auc, roc_auc, brier, recall_at_precision, each as obj of mean, ci_low, ci_high), end_to_end (obj: auc, spearman, baseline_auc, baseline_spearman), limitations (list[str]), versions. Dagim commits a realistic example file on October 24 so the evidence panel can be built before the real numbers exist.

### C3.7 Environment variable names

| Name | Used by | Meaning |
| --- | --- | --- |
| AWS_REGION | api, worker, scripts | eu-central-1 |
| IMPACTMAP_DATA_BUCKET | api, worker | data bucket name |
| IMPACTMAP_JOBS_TABLE, IMPACTMAP_CACHE_TABLE | api, worker | table names |
| IMPACTMAP_WORKER_FUNCTION | api | worker function name |
| IMPACTMAP_DATA_VERSION, IMPACTMAP_MODEL_VERSION | api, worker | active versions |
| IMPACTMAP_ALLOWED_ORIGIN | api | the one browser origin allowed by CORS |
| LOG_LEVEL | all | INFO by default |
| VITE_USE_MOCKS | web (dev only) | true to use the mock server |

Secrets never go in these. They go in Parameter Store (P1), and are read at run time.

## C4. Dependency rules (what may import what)

- impactmap_core imports only the standard library, NumPy, SciPy, LightGBM and Pydantic. It never imports boto3, FastAPI, or anything that touches a network or a file path outside its arguments. This is what makes the engine testable on a laptop.

- services/api and services/worker import impactmap_core. They are the only code that talks to S3, DynamoDB and Lambda. The API never runs the engine; it only creates jobs and reads results.

- pipeline and ml import impactmap_core (especially features.py, so training and serving compute features the same way). They never import from services.

- infra imports nothing from the Python packages. It only references folders (services/worker for the image, web/dist for the site).

- web imports no Python and no code from other folders. Its only link to the backend is contracts/openapi.yaml (generated types) and /config.json.

- Nothing imports from tests.

web  ->  (HTTP, contract only)  ->  services/api  ->  impactmap_core
                                    services/worker -> impactmap_core
pipeline, ml  ->  impactmap_core                 infra -> (folders only)

## C5. Git rules

- Branches: main is protected. Work in branches named type/owner-topic, for example feat/anon-scenario-panel, fix/dagim-snap-distance, docs/yagi-data-catalog.

- Commit messages: start with feat:, fix:, docs:, test:, chore:, infra: or data:, then a short sentence in present tense. Example: feat: add ranking table with sortable columns.

- Pull requests: one PR per task, small, with the template filled in. CI must be green. Dagim reviews Anon's and Yagi's PRs; Anon reviews Dagim's PRs that touch contracts or anything the web app consumes. Review turnaround target: two hours in working time.

- Merging: squash merge. Delete the branch after.

- Never commit: keys, tokens, .env files, raw data, large files (over 5 MB). Large artifacts go to the data bucket, not Git. gitleaks runs in CI and also as a local pre-commit hook.

- Everyone commits from their own account every day. The history is read by judges.

- Conflicts: if two people need the same file, the owner in C2 merges first and the other rebases. Ask in chat before touching someone else's folder.

- Pull request template (.github/pull_request_template.md): What this changes; Which task (module and item); How I tested it; Contract impact (none, or what changed); Screenshots if it is a screen.

## C6. Shared configuration files

pyproject.toml (root)

[tool.ruff]
line-length = 100
target-version = 'py312'

[tool.ruff.lint]
select = ['E', 'F', 'I', 'B', 'UP']

[tool.pytest.ini_options]
testpaths = ['packages', 'pipeline', 'services']
addopts = '-q'

.python-version: 3.12  ·  .nvmrc: 22 (a current long-term-support Node release; Node 20 is past its end of life [verify on nodejs.org if you prefer 24]).

.env.example (copy to .env for local work; .env is gitignored)

AWS_REGION=eu-central-1
IMPACTMAP_DATA_BUCKET=impactmap-data-ACCOUNTID
IMPACTMAP_JOBS_TABLE=impactmap-jobs
IMPACTMAP_CACHE_TABLE=impactmap-cache
IMPACTMAP_WORKER_FUNCTION=impactmap-worker
IMPACTMAP_DATA_VERSION=d20261025a
IMPACTMAP_MODEL_VERSION=m20261026a
IMPACTMAP_ALLOWED_ORIGIN=http://localhost:5173
LOG_LEVEL=INFO

Makefile targets (Dagim creates; each line under a target must start with a TAB)

| Target | Runs |
| --- | --- |
| make setup | creates the Python virtual environment and installs requirements-dev.txt and the local packages |
| make lint | ruff check . and, in web/, npm run lint |
| make test | pytest for Python and, in web/, npm test |
| make synth | cdk synth for all stacks, including the cdk-nag checks |
| make deploy | cdk deploy --all (normally done by CI, not by hand) |
| make smoke | scripts/smoke.sh against the live URL |
| make destroy | cdk destroy --all (teardown, section D11) |

## C7. Progress files (MODULE template)

Each person keeps their MODULE files in docs/ current. They are how the mentors, and the rest of the team, see what is finished. Update them in the same pull request as the work.

# MODULE_NAME  (owner: NAME)

## Status
Not started / In progress / Done / Blocked (reason)

## What is built
- item, file path, date

## Contract notes
- anything other modules must know

## How to test
- exact command or clicks

## Known issues
- item, severity, plan

Files: MODULE_SETUP, MODULE_INFRA, MODULE_DATA, MODULE_ML, MODULE_ENGINE, MODULE_API belong to Dagim; MODULE_WEB to Anon; MODULE_SUPPORT to Yagi.

## C8. Working with an AI coding assistant without creating conflicts

The rules below apply to Dagim and Anon. Yagi's tasks do not need an AI assistant, and if he uses one, he must follow the same rules.

- One file or one function per request. Never ask for the whole application.

- Always paste the context packet first (below), then the exact contract tables the task touches, then the BUILD SPEC for the task.

- Forbid invention. The packet says: do not add endpoints, fields or libraries that are not listed. If something seems missing, the assistant must stop and say what is missing.

- Ask for the assumptions the assistant made, and compare them with the contracts before accepting the code.

- Run it before committing: lint, tests, and for screens, look at it in a browser at phone width and laptop width.

- Keep names exact. If the assistant renames a field to camelCase, reject it.

- Never paste secrets into the assistant. Replace them with placeholders.

Context packet (copy this at the start of every AI session)

Project: ImpactMap AI, a flood road-access impact system for Ethiopia, built for the AWS Community Day 2026 hackathon. I am working on TASK_NAME in the folder FOLDER.
Stack (do not change): Python 3.12 on AWS Lambda (x86_64), FastAPI + Mangum for the API, a Lambda container image for the worker, DynamoDB, S3, CloudFront, API Gateway HTTP API, AWS CDK in Python. Web: React + TypeScript + Vite + Tailwind CSS v4 + TanStack Query + Zustand + MapLibre GL JS + PMTiles. Everything must stay within free tiers.
Rules: use only the endpoints, field names, enum values and file paths in the pasted contract. All JSON field names are snake_case. Coordinates are [longitude, latitude]. Do not add libraries, endpoints or fields that are not listed. If something is missing or unclear, stop and ask me instead of guessing. Keep code small, typed, and tested. Do not rename anything. Explain your assumptions at the end.
Never include or ask for secrets.

# PART A. ANON (frontend lead)

You own the web application: everything the judge and the user see. You also own the map data hosting check for the basemap, the mock server, the web tests, phone performance and the demo flow. You never need AWS access: Dagim deploys, you push to GitHub and CI does the rest. Until the real API exists (October 25) you work against a mock server built from the contract examples, so you are never waiting.

## A1. Your folders and what you do not touch

You own /web and /tests/e2e. You do not touch /services, /packages, /pipeline, /ml, /infra or /contracts. If you need a contract change, write it in the team chat to Dagim; he changes the contract and tells you.

web/
  package.json  vite.config.ts  tsconfig.json  eslint.config.js  index.html
  public/config.json                 local development defaults (see A3)
  public/dev-data/                   local copies of map data (gitignored)
  src/
    main.tsx  App.tsx  index.css     index.css contains: @import 'tailwindcss';
    config.ts                        loads /config.json before the app renders
    api/       client.ts  schema.d.ts (generated, committed)  hooks.ts
    state/     useAppStore.ts
    lib/       manualScenario.ts  format.ts  colors.ts  mapStyle.ts
    map/       MapView.tsx  layers.ts  paintResults.ts  useMapSelection.ts
    components/ TopBar.tsx  EvidenceBadge.tsx  Legend.tsx  ProbabilityBar.tsx
               RankDelta.tsx  QualityFlag.tsx  Disclaimer.tsx
    panels/    ScenarioTab.tsx  ResultsTab.tsx  CompareTab.tsx  EvidenceTab.tsx
               FacilityDrawer.tsx  SegmentDrawer.tsx  CascadeBar.tsx  WhatIfBasket.tsx
    pages/     ExplorerPage.tsx  AboutPage.tsx
    i18n/      index.ts  en.json  (am.json later)
    mocks/     browser.ts  handlers.ts
  tests/unit/                        Vitest
tests/e2e/                           Playwright (repo root)

## A2. TODAY: one-time manual setup

### A2.1 MANUAL: install and check

- Node.js 22 (use nvm, then nvm install 22; node --version must print v22.x). Vite needs Node 20.19 or 22.12 or newer [verify at vite.dev if you use a newer Vite].

- Git, a code editor, and Chrome or Edge plus Firefox for testing.

- Clone the repository after the mob session. Create a branch: git checkout -b feat/anon-web-scaffold.

- Install Playwright browsers later with npx playwright install (about a few hundred MB).

### A2.2 MANUAL: create the app (run in the repository root; the web folder exists but is empty)

npm create vite@latest web -- --template react-ts
cd web
npm install
npm install react-router @tanstack/react-query zustand maplibre-gl pmtiles @protomaps/basemaps recharts react-i18next i18next openapi-fetch
npm install -D tailwindcss @tailwindcss/vite openapi-typescript msw vitest @testing-library/react @testing-library/jest-dom jsdom @playwright/test prettier
npx msw init public/ --save

Then:

- Tailwind CSS v4: in vite.config.ts import tailwindcss from '@tailwindcss/vite' and add tailwindcss() to the plugins list next to the React plugin. In src/index.css the first line is @import 'tailwindcss'; (there is no tailwind.config file in v4 unless you need one).

- package.json scripts (names are fixed because CI calls them): dev (vite), build (tsc -b && vite build), lint (eslint .), test (vitest run), gen:api (openapi-typescript ../contracts/openapi.yaml -o src/api/schema.d.ts), e2e (playwright test).

- .gitignore in web: node_modules, dist, public/dev-data.

- Commit the scaffold, open a pull request, and re-enable the web job in CI (Dagim commented it out).

### A2.3 The two lines that make the map work with PMTiles (exact code; keep once, in src/map/MapView.tsx)

import maplibregl from 'maplibre-gl';
import { Protocol } from 'pmtiles';

const protocol = new Protocol();
maplibregl.addProtocol('pmtiles', protocol.tile);

### A2.4 MANUAL: the basemap file (Day-1 check 10, your job today)

The background map is a single file, a PMTiles archive cut out of the free Protomaps basemap. It is hosted by us, so there is no tile server and no key.

- Install the pmtiles command-line tool: open the go-pmtiles releases page on GitHub (github.com/protomaps/go-pmtiles/releases), download the archive for your operating system, unpack it, and put the pmtiles program somewhere on your PATH. Check: pmtiles --help.

- Find a recent daily build: open maps.protomaps.com/builds in a browser and copy the address of a build from the last seven days (older ones are deleted [checked: the bucket keeps the past week]). It looks like https://build.protomaps.com/YYYYMMDD.pmtiles.

- Do a dry run first to see the size (Ethiopia's rough bounding box: west 32.9, south 3.3, east 48.1, north 15.0):

pmtiles extract https://build.protomaps.com/YYYYMMDD.pmtiles ethiopia.pmtiles --bbox=32.9,3.3,48.1,15.0 --maxzoom=10 --dry-run

- If the estimated size is under about 150 MB, run the same command without --dry-run. If it is larger, lower --maxzoom to 9. Each extra zoom level roughly doubles the size [checked]. Our own road layer provides the detail at high zoom, so the basemap does not need to go deeper.

- Verify: pmtiles show ethiopia.pmtiles, and drag the file onto the viewer at maps.protomaps.com to see it.

- Give the file to Dagim through a shared drive link (do not commit it). He uploads it to the data bucket as data/basemap/ethiopia.pmtiles. For local work, copy it to web/public/dev-data/basemap/ethiopia.pmtiles.

- Labels and icons: the basemap style needs font files and sprites. For now use the Protomaps hosted assets (they are static files and free): glyphs https://protomaps.github.io/basemaps-assets/fonts/{fontstack}/{range}.pbf and sprite https://protomaps.github.io/basemaps-assets/sprites/v4/light [verify these addresses on the Protomaps basemaps documentation]. If they fail, remove the symbol layers from the style so the map still draws without text.

- Attribution text for the map: © OpenStreetMap contributors, Protomaps. Always visible.

## A3. Contracts you consume (read C3 again, especially these)

- /config.json is fetched once at startup, before anything renders. Local development uses web/public/config.json with api_base_url pointing to the live API (or the mock) and data_base_url pointing to /dev-data. data_base_url ends with /data and has no trailing slash; api_base_url has no trailing slash.

- Map data addresses (all built from config): basemap at data_base_url plus /basemap/ethiopia.pmtiles; roads at data_base_url plus / plus data_version plus /tiles/roads.pmtiles; facilities and communities at the same folder as .geojson files.

- Road tiles contract: the vector layer is named roads. Every road feature has the numeric feature id equal to its segment_id. This lets you color roads with feature state and no extra join.

- Facilities and communities are GeoJSON sources with promoteId set to facility_id and community_id, so feature state works with their string ids.

- Results: GET /results/{cache_key} for the summary; GET /results/{cache_key}/segments for the columnar arrays (only segments with probability at least 0.005 are listed; every other segment is 0).

- All field names are snake_case as delivered. Do not convert them.

- Feature flags come from config.features. If correlated_mode, landslide, forecast or accounts is false, the matching control is hidden or disabled with a short explanation.

Road paint code (exact names; this is the contract between the tiles, the API and your layer):

map.addLayer({
  id: 'roads-risk',
  type: 'line',
  source: 'roads',
  'source-layer': 'roads',
  paint: {
    'line-color': ['step', ['coalesce', ['feature-state', layerMode === 'closure' ? 'closure_prob' : 'exposure_prob'], 0],
      '#cbd5e1', 0.05, '#fde68a', 0.2, '#f59e0b', 0.4, '#dc2626', 0.7, '#7f1d1d'],
    'line-width': ['step', ['coalesce', ['feature-state', layerMode === 'closure' ? 'closure_prob' : 'exposure_prob'], 0],
      1, 0.05, 2, 0.2, 3, 0.4, 4, 0.7, 5],
  },
});
// painting one segment from the segments response:
map.setFeatureState({ source: 'roads', sourceLayer: 'roads', id: segmentId }, { exposure_prob: e, closure_prob: c });

Color and width both increase with risk, so the map still reads for people who cannot tell the colors apart. The five classes (below 5, 5 to 20, 20 to 40, 40 to 70, above 70 percent) are the same for roads, facilities and communities, and the legend must show them. When a new result arrives, first clear the feature state of all previously painted segment ids, then paint the new ones in chunks of about 2,000 per animation frame so the page does not freeze.

## A4. The application: BUILD SPEC (screens, tabs, behavior)

Give each component below to an AI assistant separately, with the context packet (C8) and the contract tables it uses. Build in the order of the task list in A9.

### A4.1 Routes

- / the Explorer (the main screen, everything below).

- /s/:cache_key the Explorer opened on the Results tab for that result (shareable link, E7).

- /about the About page (A4.11).

### A4.2 Explorer layout

Laptop (width 1024 pixels or more): a top bar 56 px high; a left panel 380 px wide with four tabs: Scenario, Results, Compare, Evidence; the map fills the rest; a right drawer 400 px wide slides over the map for facility or segment details; a cascade bar appears at the bottom of the map when a demo is chosen.

Phone (under 768 px): the map fills the screen; the tabs live in a bottom sheet with three positions (peek, half, full); drawers open as full-height sheets with a clear close button; the top bar shows only the name, the evidence badge and a menu.

### A4.3 Top bar

Product name ImpactMap AI; the region display name from /regions; a hazard badge (Flood); the evidence badge from evidence_level with exact words Validated, Limited or Heuristic (text, plus a distinct shape so color is never the only signal); a small chip with the model and data versions that links to /about; a language switch (English only until am.json exists, then hidden if the file is missing); the About link.

### A4.4 Scenario tab

- Library: cards from GET /scenarios/library. Each card shows title, short description, a badge Replay or Manual, and a Run button. A card whose item has demo set to true also shows Play cascade (A4.9). The library includes one item with the slug baseline-dry (no rain) for use as the comparison baseline.

- Build your own (a form whose fields match the Scenario table in C3.6 one to one):

  - Storm total in mm (slider 10 to 400) and Duration in days (1 to 10).

  - Storm shape: four choices (Even, Front-loaded, Mid-peak, Back-loaded), each with a tiny bar picture.

  - Previous month: Dry, Normal, Wet.

  - Spatial pattern: Uniform, Gradient (direction dial 0 to 359, ratio slider 0.2 to 1.0), or Storm cell (click the map to place the center; radius slider 5 to 200 km).

  - Start date (default today).

  - Assumed closure (slider 0 to 1, step 0.05, helper text: how often a flooded road is treated as closed; default 1).

  - Failure mode: Independent. The Correlated option is shown disabled when the flag is off.

  - Advanced fold: number of samples (100, 200, 400) and seed.

- Daily rainfall preview: a bar chart of the daily_rain_mm array that will be sent, so the user sees exactly what the model receives. A text line under it states the total.

- Run button: sends POST /scenarios. While waiting show the three states Queued, Running, Done. Poll GET /jobs/{job_id} every second for the first 10 seconds, then every 3 seconds, until done or failed or 120 seconds have passed. On failed or timeout show the message from the error shape and a Try again button. On a validation error highlight the field named in the error.

Manual controls to daily array (exact rule; the backend uses the same rule for library items): for a duration N and a total T, give day k (counting from 0) a weight w_k, then daily_rain_mm[k] = T times w_k divided by the sum of all weights. Weights: even: 1. front_loaded: N minus k. back_loaded: k plus 1. mid_peak: the smaller of (k plus 1) and (N minus k). The previous-month choice sets antecedent_30d_mm to 40 (dry), 120 (normal) or 220 (wet). Round daily values to 1 decimal. Golden tests for your unit tests: T 120, N 4, front_loaded gives 48, 36, 24, 12; T 60, N 4, mid_peak gives 10, 20, 20, 10; T 60, N 3, back_loaded gives 10, 20, 30; T 120, N 5, even gives 24 five times.

### A4.5 Results tab

- Summary cards (from region_totals): estimated people cut off (mean, with the range p10 to p90 written as a range), estimated people with degraded access, and expected number of isolated facilities. A line under the cards: Estimated access loss under the assumed closures. Not a forecast.

- Ranking table (from ranking): columns Rank, Facility (name, level icon), Isolation probability (a bar with the p10 to p90 range), Estimated people affected, Score, Rank change (arrow and number, or a dash), Flags (poor baseline access, data-quality flags). Sort by any column; filter by level; search by name. Clicking a row selects the facility: the map flies to it and the facility drawer opens. Show the three raw components next to the score (a small expandable row) because the score is relative to this region.

- Top communities (from top_communities) in a collapsed section with the same style.

- Empty state: Run a scenario to see results.

### A4.6 Compare tab

Two dropdowns, A and B, listing results from this session plus the library items (including Baseline). A table view shows the region totals side by side with deltas, and the list of rank changes from GET /compare. A swipe view (two synced maps and a slider) is in the cut-line: build the table first, the swipe only if time remains.

### A4.7 Evidence tab

Reads the static evaluation file (evidence/evaluation.json, shape in C3.6). Shows: the evidence badge and the label rung in plain words (L0 Validated on several observed floods; L1 and L2 Limited validation; L3 Heuristic); a table of model versus baselines for each metric with the interval drawn as a small bar with whiskers; the end-to-end sentence (how well predicted facility isolation matched what the observed flood extent implied); the list of events with their split; the limitations list; the versions. Observed-versus-predicted map overlay is P1. Until the real file exists, build it against the example file Dagim commits on October 24.

### A4.8 Map behavior

- Layers: basemap; roads colored by risk (A3); facilities (circle size by level: hospital largest, then health_center, then clinic; fill color by the same five classes using p_isolation from the result; a thicker outline when the flags field is set); communities (circle size by the square root of people_est, translucent, color by p_cut_off). A layer panel has toggles for each, a switch between Flood exposure probability and Assumed closure for roads, and the legend.

- Hover a road: highlight it and show a tooltip with name and road class. Click a road: open the segment drawer (A4.10). Click a facility: open the facility drawer. Click a community: a small card with people_est, p_cut_off, p_degraded, baseline minutes and flags. Selection is synchronized with the ranking table in both directions.

- The alternative route (facility drawer button) draws alt_route.geometry as a dashed line layer named alt-route.

- Data-quality hatching on low-road-density areas is P1; in P0 the flags appear in rows, drawers and cards.

### A4.9 Cascade bar (the signature demo feature)

Shown at the bottom of the map when a library item with demo set to true is chosen (Play cascade). Data: GET data_base_url/demo/index.json lists the demos; each step is data_base_url/demo/SLUG/step_N.json (shape in D9.4: step, day_label, rain_cumulative_mm, cache_key, summary_url, segments_url, narration, changes).

- Controls: Play and Pause, a step slider from 1 to n_steps, and a speed choice (1 second or 2 seconds per step).

- On opening, preload all steps (their summary and segments files) so playback is instant and does not depend on the network on stage.

- At each step: repaint roads from that step's segments file; update facility and community colors from that step's summary; show the day label, the cumulative rainfall and the narration sentence in a card above the bar; show the changes list as small lines such as Clinic X: rank 14 to rank 3.

- The ranking table (Results tab) follows the current step while the cascade is active, and returns to the normal result when the cascade is closed.

- A Close button leaves the cascade and restores the previously selected result.

### A4.10 Facility drawer, segment drawer and what-if

Facility drawer (opens on a facility click or a ranking row click; data from the ranking row plus GET /facilities/{facility_id}/explain?cache_key=...):

- Header: name, level, quality flags.

- Key numbers: isolation probability with its p10 to p90 range, estimated people affected, score with the three raw components, baseline minutes and, if poor_baseline_access is true, a plain note: This place already has long travel times to a hospital without any flood, so it is shown separately from flood damage.

- Why: the sentences list from the explain response, then up to three segment chips; clicking a chip zooms to the segment and highlights it.

- Alternative route: if alt_route is not null, a button that draws it and shows its minutes; if null, the text No surviving route to another hospital in the typical sample.

- Data quality: source, snap distance in metres, flag text.

- Loading skeleton and an error line with Retry.

Segment drawer (opens on a road click; data from GET /segments/{segment_id}/explain?cache_key=...): name, road class, length, exposure probability and assumed closure probability, the top reasons as plain English with a small bar each (the label field is already in plain English), and two buttons: Assume closed and Assume open (protect this road).

What-if basket (WhatIfBasket.tsx): a small floating panel listing the segments the user forced closed or open, each with a remove button, a count, and an Apply button. Apply sends POST /whatif with base_cache_key set to the current result and the two lists. The returned job is polled like any scenario. When it finishes, the new result becomes current and a banner says What-if: N changes versus the original, with a Before and after card (people cut off, difference) and a Back to original button. The what-if result keeps its own cache_key, so it can be compared in the Compare tab.

### A4.11 About page (/about)

Sections: What this is and is not (text from Yagi, section Y2); The three numbers (a table: Flood exposure probability, Assumed closure, Estimated access loss; what each means and where it comes from; text from Yagi); Assumptions (rendered from the assumptions object of the current result and from /meta: speeds by road class, closure factor, degraded ratio 2.0, poor-baseline threshold 120 minutes); Limitations (list, text from Yagi, taken from the model card); Data and licences (a table rendered from /meta or a static file built from docs/data-catalog.csv); API for developers (a short paragraph and a link to the interactive docs at api_base_url plus /docs, and a copyable curl example for POST /scenarios).

Footer on every page: Prioritization aid for human assessment. Not a forecast. Map data © OpenStreetMap contributors. Basemap by Protomaps. Population: WorldPop. Rainfall: CHIRPS. Elevation: Copernicus DEM. Each is a link to its licence.

### A4.12 UI strings (exact wording for the terms that carry meaning)

All text lives in src/i18n/en.json under stable keys so that Yagi can translate later; no hard-coded strings in components. These terms are fixed and must not be paraphrased in the UI:

| Key | English text |
| --- | --- |
| disclaimer | Prioritization aid for human assessment. Not a forecast. |
| exposure_label | Flood exposure probability |
| closure_label | Assumed closure |
| access_loss_label | Estimated access loss under the assumed closures |
| people_label | estimated people |
| poor_baseline | Long travel time even without a flood |
| evidence_validated, evidence_limited, evidence_heuristic | Validated, Limited, Heuristic |

### A4.13 States every screen must handle

Loading (skeleton, not a blank screen); empty (no result yet); error (message from the Error shape, the request_id in small text, a Retry button); offline or API down (a banner: Live computation is unavailable. Demo scenarios still work.; the cascade and library demos keep working because they are static files); slow job (after 20 seconds show: Still working. New scenarios can take up to a minute.); rate limited (429: Too many requests, wait a moment).

### A4.14 Accessibility and performance requirements

- Keyboard: every control reachable; visible focus; the ranking table is the keyboard alternative to clicking the map. Touch targets at least 44 px. Text contrast at least 4.5 to 1. Color is never the only signal (we also use width, shape, text). Honour reduced-motion for the cascade.

- Every chart has a text summary. The map has an accessible label.

- Performance: the first load under 3 seconds on a 4G connection; load the Compare, Evidence and About code lazily (React lazy and Suspense); never re-create the map when state changes; throttle hover handlers; paint in chunks (A3). Check a mid-range Android phone on mobile data once on October 25 and once on October 27 and write the timings in MODULE_WEB.md.

## A5. State and data layer (BUILD SPEC)

- config.ts: fetch /config.json first; render the app only after it is loaded; on failure show a clear error page. Export typed values.

- api/client.ts: an openapi-fetch client created with api_base_url, typed by src/api/schema.d.ts (generated by npm run gen:api from contracts/openapi.yaml; the generated file is committed; regenerate whenever the contract changes).

- Server data only in TanStack Query, with these keys: meta; library; job with the job_id; result with the cache_key; segments with the cache_key; facility-explain with the facility_id and cache_key; segment-explain with the segment_id and cache_key; compare with a and b; evidence with the data_version; demo-index; demo-step with the slug and step. Results are immutable for a given cache_key, so give them an infinite stale time.

- UI state only in Zustand (state/useAppStore.ts): currentCacheKey, baseCacheKey (for what-if banners), layerMode (exposure or closure), selectedFacilityId, selectedSegmentId, whatIf (closed set and open set), comparePair, cascade (slug, step, playing), activeTab, drawerOpen.

- No component calls fetch directly; all calls go through api/hooks.ts.

## A6. Mock server (BUILD SPEC, today)

Mock Service Worker in src/mocks, turned on when VITE_USE_MOCKS is true. Handlers return the files in contracts/examples for every endpoint in C3.5. Make these behaviours switchable from a small developer menu or query parameters: POST /scenarios returns 200 at once (cached); returns 202 and then the job goes queued, running, done over about 6 seconds (to test the progress UI); returns 400 with a field error; returns 429; returns 500; the network is offline. This is how the screens are built and tested before the real API exists.

## A7. Tests

- Vitest (unit): the manual-controls conversion with the golden values in A4.4; the paint helper (it clears old ids and paints new ones); the formatters (probability to percent, people to rounded text with the word estimated); the ranking sort and filter.

- Component tests (Testing Library): the Scenario form validation messages; the ranking table sorting; the facility drawer renders the three states.

- Playwright (tests/e2e), run against the mock server in CI and against the live URL before the demo: (1) open the app, run a library scenario, see the ranking, open the top facility, see the why text; (2) play the cascade and see the narration change; (3) assume a road closed, apply what-if, see the before and after card; (4) the API-down banner appears when the API is offline and the demo cascade still plays.

## A8. CI for the web

The web job in ci.yml runs npm ci, npm run lint, npm test and npm run build inside /web. The build must work with no environment variables, because the app reads /config.json at run time. Keep public/config.json for development only; the deployed one is written by Dagim's ConfigStack.

## A9. Your task order (do them in this order; each is one pull request)

| # | Task | Done when | Target time |
| --- | --- | --- | --- |
| T1 | Scaffold and tooling (A2), CI web job on | CI green, empty page loads | Oct 23 morning |
| T2 | Basemap extract and local hosting check (A2.4) | File produced, shared with Dagim, map shows locally | Oct 23 noon |
| T3 | Config loader, API client, Zustand store, TanStack Query setup | The app prints the /health result | Oct 23 afternoon |
| T4 | Mock server (A6) | All endpoints served from examples; switchable cases work | Oct 23 evening |
| T5 | Map base: basemap, roads, facilities and communities from dev data, legend, layer panel | Roads draw from a local test PMTiles file; legend correct | Oct 24 morning |
| T6 | Scenario tab: library, builder, rainfall preview, conversion function with tests | Golden tests pass | Oct 24 afternoon |
| T7 | Run and poll flow with all states (A4.4 step 4) | Mock 202 sequence reaches Done; errors shown | Oct 24 evening |
| T8 | Paint results on the map (A3) and Results tab with ranking table | Example result colors the map; sorting works | Oct 25 morning |
| T9 | Facility drawer, segment drawer, what-if basket | The three drawers and the before and after card work on mock data | Oct 25 afternoon |
| T10 | Switch to the live API (change config only); fix contract mismatches with Dagim | Scenario runs end to end on the live URL | Oct 25 evening |
| T11 | Cascade bar (A4.9) | Demo plays with preloaded steps | Oct 26 morning |
| T12 | Evidence tab and Compare table | Real evaluation.json renders | Oct 26 midday |
| T13 | About page, i18n wiring, static pages with Yagi's text | No hard-coded strings; texts shown | Oct 26 afternoon |
| T14 | Performance, accessibility, phone checks | Targets in A4.14 recorded | Oct 26 evening |
| T15 | Playwright flows, bug fixes from tester round 2 | All four flows pass | Oct 27 |
| T16 | Swipe compare (cut-line item) | Only if everything above is done | Oct 27, optional |
| T17 | Data-quality hatching (cut-line item) | Only if everything above is done | Oct 27, optional |

## A10. Demo and video ownership

You own the demo flow from section 14 of the functional document. Rehearse the two-minute script until it runs with no thinking, on the laptop used on stage and on the stage network if possible. Prepare a local copy of the front end with cached demo files as the fallback. With Dagim record the video on October 27 with OBS Studio (free).

## A11. Anon final checklist

| # | Item | Status |
| --- | --- | --- |
| 1 | App scaffold, Tailwind v4, tooling, CI web job green | [ ] |
| 2 | Basemap file made, verified, handed to Dagim, loads from our bucket through CloudFront | [ ] |
| 3 | Config loader works; no environment variables needed to build | [ ] |
| 4 | Mock server covers every endpoint and the failure cases | [ ] |
| 5 | Roads, facilities, communities draw with the shared five-class legend | [ ] |
| 6 | Manual controls conversion passes the golden tests | [ ] |
| 7 | Run and poll flow shows Queued, Running, Done and all error states | [ ] |
| 8 | Results tab, ranking table (sort, filter, search), summary cards | [ ] |
| 9 | Facility drawer, segment drawer, what-if basket, before and after card | [ ] |
| 10 | Cascade bar plays with preloaded steps | [ ] |
| 11 | Evidence tab shows the real evaluation file and the evidence badge | [ ] |
| 12 | Compare table works | [ ] |
| 13 | About page and footer with disclaimer and attributions | [ ] |
| 14 | All UI text in en.json; fixed terms exact | [ ] |
| 15 | Phone check done twice; timings recorded | [ ] |
| 16 | Four Playwright flows pass | [ ] |
| 17 | Demo script rehearsed; local fallback copy ready | [ ] |
| 18 | MODULE_WEB.md up to date | [ ] |

# PART S. SCHEDULE, HANDOFFS, RISKS AND FINAL CHECKS

## S1. Day-by-day plan

Dates follow the handbook. Today is Friday October 23. The 28th is a buffer for final checks and submission before midday. Ethiopian weekend days are used as working days because the window is short; plan rest hours yourselves so that nobody is exhausted on the 27th.

| Day | Dagim | Anon | Yagi | Testers | Exit check |
| --- | --- | --- | --- | --- | --- |
| Fri Oct 23 | Setup D2 (tools, AWS, budgets, repo). 60-minute mob session. Contracts and examples pushed by 12:00. Flood-event audit and the gate at 20:00 (priority over everything except contracts). CDK bootstrap and walking skeleton as far as time allows; finishing it on the morning of the 24th is acceptable. | T1 to T4: scaffold, basemap file (to Dagim by noon), config and client, mock server. | Y0, Y1 first eight rows. | Told what is coming; no work yet. | Contracts published. Gate decided and written down. Repo, CI and branch rules exist. |
| Sat Oct 24 Checkpoint 2 (Oct 23 to 24) | Finish skeleton (live fake API, CORS proven). Graph, facilities, communities, terrain features, labels. Baselines B0 and B1. Core package and engine with tests. Send facilities.csv to Yagi and example evaluation.json to Anon in the evening. | T5 to T7: map base, Scenario tab, run and poll flow. | Y1 event rows, Y2 draft, Y3 sheet created. | Snapping spot-check starts after the data is published. | Live fake API works from the CloudFront page. Engine tests pass. IaC deploys from CI. |
| Sun Oct 25 Checkpoint 3 starts (Oct 25 to 26) | Train, calibrate, leave-one-event-out evaluation. Real worker image. Real API replaces the fake handlers. Scenario runs end to end on the live URL (even if the model is rough). | T8 to T10: paint results, Results tab, drawers, what-if, switch to the live API. | Y4 complete. Round-1 list written. | Round 1 of testing. | A scenario runs end to end on the live URL. |
| Mon Oct 26 | Ranking, explanations, what-if, compare. Demo scenarios and cascade steps precomputed. Dashboard, alarms, budget in code (delete the manual budgets). Security tools, docs/security.md. Real evaluation.json. Feature list frozen at the end of the day. | T11 to T14: cascade, Evidence, Compare, About, strings, performance, phone checks. | Y2 finished and merged. Y3 export to docs/testing. | Facility sheet completion. | Everything in P0 works. Freeze. |
| Tue Oct 27 Checkpoint 4 (Oct 27 to 28) | Load test, teardown and redeploy test, model card, README technical parts, architecture diagram, video draft. Code freeze in the evening. | T15: Playwright flows, fixes from tester round 2, polish. Video recording with Dagim. | README skeleton check. Round-2 list. | Round 2 and break-it session. | Code freeze. Video recorded. Secret scan clean. |
| Wed Oct 28 | Final deploy from CI. Check the live URL from another network and a phone. Assemble the submission package. | Smoke test on phone and laptop. | Checklist review (S5). | Final look at the live link. | Submit by midday. The handbook gives no time of day; do not risk it. |
| Thu Oct 29 to Sat Oct 31 | P1 picks in this order: correlated mode, mitigation list. Finalist announcement is October 30; rehearsal October 31. | Pitch demo flow. | Rehearsal audience. | Rehearsal audience. | Finalist stage ready. |

Honest warning. October 25 is the hardest day: Dagim has to train the model, build the worker and connect the API on the same day. If by 14:00 on the 25th the model is not trained and evaluated, do not keep pushing: take the next rung of the fallback ladder (section 15 of the functional document), ship the baselines plus whatever model exists with an honest evidence badge, and finish the pipeline. A working end-to-end system with a modest model scores higher than a perfect model with no deployment.

## S2. Handoffs (who gives what to whom)

| # | From to | What | When | Confirmed by |
| --- | --- | --- | --- | --- |
| 1 | Dagim to Anon | CONTRACTS.md, contracts/openapi.yaml, contracts/examples | Oct 23, 12:00 | Anon builds the typed client from the file |
| 2 | Anon to Dagim | The basemap file ethiopia.pmtiles (shared drive link) | Oct 23, noon | Dagim uploads it; Anon sees it load from CloudFront |
| 3 | Dagim to Anon | Live fake API address and /config.json in place | Oct 23 evening or Oct 24 morning | Anon's page prints a response |
| 4 | Dagim to Yagi | Dataset source links (the table in Y1) now; flood-event dataset links; facilities.csv | Oct 23; Oct 24 | Yagi confirms the rows and the sheet |
| 5 | Dagim to Anon | Example evaluation.json; real evaluation.json; demo files in the data bucket | Oct 24 evening; Oct 26; Oct 26 | Evidence tab and cascade render |
| 6 | Yagi to Anon | web/src/content/about.md | Oct 26 midday | About page renders three sections |
| 7 | Yagi to Dagim | docs/data-catalog.csv complete; facility_review.csv | Oct 24 and Oct 26 | Dagim applies facility corrections and reruns the pipeline if needed |
| 8 | Anon to Dagim | A web app that builds in CI with no environment variables | Oct 24 | Deploy workflow is green |
| 9 | Yagi to Dagim and Anon | Tester findings lists | Oct 25 evening and Oct 27 evening | Everyone reads it the same night |

## S3. Cut-line (what to drop first if behind)

Drop in this order, from the top. Say so in the team chat when you drop something.

- Correlated failure mode (keep the statement that independent mode understates joint risk).

- Swipe view in Compare (keep the table).

- Data-quality hatching on the map (keep the flags in drawers and rows).

- More than one cascade demo (keep one).

- Baseline B2, the hazard-map lookup.

- More than two historical replays (keep two as a minimum).

- Observed-versus-predicted map in the Evidence tab (keep the metrics).

Never drop (these are the rubric): the deployed pipeline from CI, baselines B0 and B1, leave-one-event-out evaluation, the evidence panel, the budget alarm in code, infrastructure as code, least-privilege roles, teardown, the README, the architecture diagram and the demo video.

## S4. Risks and what we do about them

| Risk | Owner | What we do |
| --- | --- | --- |
| Too few usable flood events | Dagim | Gate tonight; fallback ladder L1 to L3; honest evidence badge; tell the mentor at Checkpoint 2. |
| Dagim is on the critical path for almost everything | Dagim | Walking skeleton first; cut-line; Anon builds on mocks so he never waits; ask Anon to take a defined small backend or CI helper job if Dagim falls behind by 14:00 on the 25th. |
| Contract mismatch between backend and web | Dagim and Anon | One contract file; examples validated against the OpenAPI file; contract changes announced; the switch from mock to live is only a config change. |
| AWS Free plan blocks a service | Dagim | Day-1 deploy test; nearest allowed service; ADR; mention at checkpoint. |
| The model does not beat the baseline | Dagim | Report it honestly; keep both in the product; evidence badge Limited. |
| Account ownership or age terms are unresolved | Dagim | Settle with the organizers today; document in docs/aws-account.md. |
| Basemap file too large | Anon | Dry run first; lower the maximum zoom; our road layer gives the detail. |
| Last-minute deploy failure | Dagim | Final deploy on the morning of the 27th as a rehearsal; submit by midday on the 28th; keep the recorded video as a fallback. |
| Tester availability | Yagi | Schedule sheet; fall back to the team testing each other's screens. |
| Stage network fails | Anon | Static cascade files, local fallback copy, recorded video. |
| Free-tier surprise | Dagim | API throttling, no paid services, budget alarms, billing page check after the load test. |

## S5. Submission checklist (assembled by Dagim; reviewed by everyone on October 28)

| # | Deliverable | Owner | Status |
| --- | --- | --- | --- |
| 1 | Public GitHub repository with commits from all members | Dagim | [ ] |
| 2 | /infra with one-command teardown, tested | Dagim | [ ] |
| 3 | Architecture diagram in the README | Dagim | [ ] |
| 4 | Live URL works from another network and a phone | Dagim and Anon | [ ] |
| 5 | README: problem, persona, where and why AI is used, setup, deploy, metrics, limits, cost, security, teardown, declared third-party items | Dagim, Yagi | [ ] |
| 6 | Model documentation: sources, preprocessing, training scripts, evaluation, model card, data catalog | Dagim, Yagi | [ ] |
| 7 | CI/CD workflows that test, build and deploy | Dagim | [ ] |
| 8 | Security evidence: no secrets in history, gitleaks, cdk-nag, IAM table | Dagim | [ ] |
| 9 | Budget alarm documented (screenshot and the code) | Dagim | [ ] |
| 10 | CloudWatch dashboard visible with logs and metrics | Dagim | [ ] |
| 11 | Video demo 2 to 3 minutes: interaction, live inference, AWS console and CloudWatch logs | Anon and Dagim | [ ] |
| 12 | All libraries, datasets and models declared with licences | Dagim, Yagi | [ ] |

Final check before submitting: open the live URL in a private window on a phone, run the demo path, open the README and click every link, and confirm the repository contains no keys.

## S6. After the deadline (the resume project continues)

P1 in order: correlated mode, landslide as a labelled heuristic, mitigation list, forecast and Telegram alerts, PDF report, accounts and the review loop, Amharic and Afaan Oromo. P2: field verification loop, offline use, retraining and drift monitoring, onboarding of new regions. After the event: rewrite the open questions from section 16 of the functional document as issues, keep the load-test and evaluation scripts in the repository, and write two or three resume bullets with real numbers (events used, metrics with intervals, cost per 1,000 scenarios, cloud services used).

## S7. When you get stuck (how to ask for help, and who to ask)

- Inside the team: post in the chat with the task ID and step number, what you did, and what you saw. Ask within 30 minutes of being stuck.

- For the manual setup steps: use this document first. If a screen or option looks different from what is written (cloud consoles change often), ask your assistant with this document available as context. Send: the step ID (for example D2.2 step 5), a screenshot or the exact error text with secrets removed, your operating system, and what you expected. Ask for the next single step, not the whole procedure again.

- For code: follow C8. Paste the context packet and the exact contract tables first.

- For mentors: prepare one line for each checkpoint: what is done, what is blocked, what you need.

- Never paste an access key, bot token or password into a chat. If you did by mistake, tell Dagim immediately: the key is revoked and replaced.